## Sheet1
ID | Date | Resource Name / Role | Planned Tasks / Deliverables | Actual Progress / Output | % Productivity (vs Plan) | Impediments / Risks Identified | Risk Category | Severity (L/M/H) | Mitigation / Action Plan | Owner | Status
1 | 13-Oct-2025 | Android Developer | Review SDK architecture, setup dev environment | Completed | 100% | None | - | - | Continue next module | PM | Closed
2 | 13-Oct-2025 | iOS Developer | Setup Xcode project, link SDK | Completed | 100% | None | - | - | Proceed to popup revamp task | PM | Closed
3 | 13-Oct-2025 | Java Backend Dev 1 | Update feedback API swagger | In Progress | 80% | API dependency from UI team | Dependency | Medium | Align in daily sync; mock response | Tech Lead | Open
4 | 13-Oct-2025 | React Developer | Prepare analytics tagging spec for web | Completed | 100% | None | - | - | Submit for review | PM | Closed
5 | 14-Oct-2025 | QA Tester 1 | SIT test case design | In Progress | 90% | Missing logout flow scenarios | Functional | Low | Add logout test cases by 15th | QA Lead | Open
6 | 15-Oct-2025 | Android New Joiner | Review onboarding docs & SDK guidelines | Completed | 100% | Ramp-up phase | Resource | Low | Assign minor bug fix tasks from 17th | Android Lead | Closed
7 | 16-Oct-2025 | Java Backend Dev 2 | Implement DB migration script | Delayed | 50% | DB env access issue | Environment | High | Escalate to DevOps; target 18th | PM | Open
8 | 17-Oct-2025 | React Deep Link Dev | Review deep link handling for feedback popup | In Progress | 75% | Awaiting API confirmation | Dependency | Medium | Backend to finalize payload by 18th | Tech Lead | Open
9 | 18-Oct-2025 | Content Developer | Update UX text & feedback copy for 7 journeys | Completed | 100% | None | - | - | Push updated JSONs to repo | PM | Closed
10 | 18-Oct-2025 | QA Tester 2 | Prepare regression suite for mobile | In Progress | 85% | SDK build delay | Schedule | Medium | Android build ETA 19th | QA Lead | Open