## Sheet1
Task ID | Task Name | Description | Owner | Start Date | End Date | Effort (Days) | Effort (Hours) | Dependencies | Acceptance Criteria
1 | Requirements Gathering | Review BRD, confirm journeys & logout flow requirements. | Architect + BA | 13-Oct-2025 | 14-Oct-2025 | 2 | 16 |  | All 7 journeys & logout flow confirmed with business sign-off.
2 | UX/UI Design Review | Review feedback popup design revamp & confirm alignment with SDK framework. | Architect + UX Team | 14-Oct-2025 | 15-Oct-2025 | 2 | 16 | Task 1 | UI mockups approved and uploaded to ADO.
3 | Adobe Analytics Event Definition | Prepare tagging matrix for popup open/submit/logout and backend events. | Architect + All | 15-Oct-2025 | 16-Oct-2025 | 2 | 16 | Task 1 | Tagging matrix signed off by analytics team.
4 | HLD & LLD Preparation | Prepare solution design, sequence diagrams, API mapping, and LLD. | Architect | 15-Oct-2025 | 17-Oct-2025 | 3 | 24 | Tasks 1-3 | HLD & LLD approved and linked to ADO.
5 | Architecture Review & Approval | Solution walkthrough with architect board and finalize design. | Architect + Devs | 17-Oct-2025 | 17-Oct-2025 | 1 | 8 | Task 4 | Architecture approval received and documented.
6 | API Contract Update | Update Swagger & define schema changes (feedbackSource, journeyType, analyticsId). | Java Dev | 20-Oct-2025 | 21-Oct-2025 | 2 | 16 | Task 5 | Swagger published; approved by architect.
7 | Feedback API Enhancement | Implement feedback API changes for journeyType/logout and analytics. | Java Dev | 22-Oct-2025 | 28-Oct-2025 | 5 | 40 | Task 6 | API tested successfully with updated payloads.
8 | Database Schema Modification | Add new columns (feedback_type, source, analytics_id) and migration script. | Java Dev | 29-Oct-2025 | 30-Oct-2025 | 2 | 16 | Task 7 | DB migration executed & rollback tested.
9 | Backend Adobe Analytics Integration | Push server-side feedback events to Adobe Analytics endpoint. | Java Dev | 31-Oct-2025 | 04-Nov-2025 | 3 | 24 | Task 8 | Analytics payload verified in Adobe workspace.
10 | OCP Deployment Setup | Create/update YAMLs for DEV, SIT, and UAT; configure pipelines. | Java Dev | 05-Nov-2025 | 06-Nov-2025 | 2 | 16 | Task 9 | OCP pods deployed successfully in DEV.
11 | Backend Unit & Integration Testing | Conduct unit, integration, and regression testing. | Java Dev | 06-Nov-2025 | 07-Nov-2025 | 2 | 16 | Task 10 | All unit tests passed, coverage ≥ 85%.
12 | Android SDK - Feedback Popup UI | Implement new feedback popup for 7 journeys. | Android Dev | 20-Oct-2025 | 28-Oct-2025 | 7 | 56 | Task 5 | UI matches design; verified on devices.
13 | Android SDK - Logout Feedback Reuse | Implement popup reuse logic for logout. | Android Dev | 29-Oct-2025 | 31-Oct-2025 | 3 | 24 | Task 12 | Logout feedback works without regression.
14 | Android SDK - Adobe Analytics Integration | Integrate analytics for open/submit/logout popup events. | Android Dev | 01-Nov-2025 | 04-Nov-2025 | 3 | 24 | Task 13 | Analytics events visible in Adobe dashboard.
15 | Android SDK - Unit Testing & Packaging | Unit test SDK, perform code review, create SIT build. | Android Dev | 05-Nov-2025 | 06-Nov-2025 | 2 | 16 | Task 14 | Code coverage ≥90%, build approved for SIT.
16 | iOS SDK - Feedback Popup UI | Implement new feedback popup for 7 journeys. | iOS Dev | 20-Oct-2025 | 28-Oct-2025 | 7 | 56 | Task 5 | Popup matches UI spec; tested on latest iOS version.
17 | iOS SDK - Logout Feedback Reuse | Integrate popup reuse logic on logout. | iOS Dev | 29-Oct-2025 | 31-Oct-2025 | 3 | 24 | Task 16 | Logout feedback trigger verified; no app crash.
18 | iOS SDK - Adobe Analytics Integration | Integrate Adobe SDK and event hooks for popup actions. | iOS Dev | 01-Nov-2025 | 04-Nov-2025 | 3 | 24 | Task 17 | Analytics events captured successfully in test suite.
19 | iOS SDK - Unit Testing & Packaging | Unit test SDK and generate SIT build. | iOS Dev | 05-Nov-2025 | 06-Nov-2025 | 2 | 16 | Task 18 | iOS SDK build validated and delivered to QA.
20 | Back Office UI Enhancement | Add logout feedback score and analytics filter to dashboard. | React Dev | 27-Oct-2025 | 31-Oct-2025 | 5 | 40 | Task 7 | Logout score displayed correctly; filter works.
21 | Web Adobe Analytics Integration | Add tracking for dashboard interactions and feedback analytics. | React Dev | 03-Nov-2025 | 06-Nov-2025 | 3 | 24 | Task 20 | Analytics dashboard tracking validated.
22 | UI & Regression Testing | Perform regression and cross-browser tests for updated dashboard. | React Dev + QA | 07-Nov-2025 | 08-Nov-2025 | 2 | 16 | Task 21 | No UI defects; test report signed off.
23 | System Integration Testing (SIT) | E2E testing of mobile, backend, and portal integrations. | QA + All | 10-Nov-2025 | 14-Nov-2025 | 5 | 40 | Tasks 15,19,22 | SIT pass with no critical defects.
24 | User Acceptance Testing (UAT) | Business UAT with stakeholders; track feedback in ADO. | QA + Business | 17-Nov-2025 | 20-Nov-2025 | 4 | 32 | Task 23 | UAT sign-off received.
25 | Operational Acceptance Testing (OAT) | Validate infra readiness, logging, performance, and rollback plan. | QA + DevOps | 20-Nov-2025 | 21-Nov-2025 | 2 | 16 | Task 24 | OAT certificate signed by operations.
26 | Architecture & SIA Approval | Conduct final review with architecture & security team. | Architect + Devs | 19-Nov-2025 | 20-Nov-2025 | 2 | 16 | Task 24 | SIA & architecture approvals uploaded to ADO.
27 | Release Packaging | Bundle Android/iOS SDKs, React build, and backend artifacts. | All Devs | 21-Nov-2025 | 22-Nov-2025 | 2 | 16 | Tasks 25,26 | All builds verified and tagged in Git.
28 | Production Deployment | Deploy backend to OCP PROD and web to production environment. | Java Dev + React Dev | 22-Nov-2025 | 22-Nov-2025 | 1 | 8 | Task 27 | Prod deployment verified; smoke tests passed.
29 | ADO Work Item Closure | Close ADO tasks, attach test evidence, and release note. | All + PM | 22-Nov-2025 | 22-Nov-2025 | 1 | 8 | Task 28 | All ADO items closed with documentation attached.
30 | ADO Sprint Setup | Create sprints, assign resources, and link work items. | PM | 13-Oct-2025 | 14-Oct-2025 | 2 | 16 |  | All work items linked to sprints in ADO.
31 | Daily Scrum & Progress Tracking | Conduct daily scrums and update sprint board. | PM + All | 13-Oct-2025 | 22-Nov-2025 | 30 | 240 | Task 30 | Scrum updates recorded daily; sprint burn-down maintained.
32 | Weekly Status Reports | Share progress with stakeholders and update in ADO. | PM | 17-Oct-2025 | 22-Nov-2025 | 6 | 48 | Task 31 | Weekly status reports uploaded and approved.
33 | Documentation Updates | Maintain design docs, release notes, and test summary. | PM + All | 20-Nov-2025 | 22-Nov-2025 | 3 | 24 | Tasks 26-28 | All docs archived in ADO & Confluence.